## Contents
SAMPLE Summer Learning Program Planner
Contents
1. Overview
2. Program Team Planner
3. Asset Mapping
4. Needs Assessment
5. Operations Planner
6. Budget Planner
7. Program Schedule
8. Field Trip Planner
9. Intentional Design Planner
10. Staffing Planner
11. Intentional Recruitment Planner
12. Logic Model
13. Continuous Improvement Planner
About This Resource The Summer Learning Program Planner was developed as part of the U.S. Department of Education’s 21st CCLC Summer Learning Initiative in 2016 and was used by 40 participating subgrantees in seven states. The Initiative supported students’ academic growth and development during the summer months and enhanced the ability of 21st CCLC program leaders, staff, and volunteers to design and manage high-quality programs all year long. This resource was adapted in 2024 by the Nita M. Lowey 21st Century Community Learning Centers (21st CCLC) National Technical Assistance Center (NTAC), funded under a grant from the U.S. Department of Education (Department) and administered by Synergy Enterprises, Inc. under Cooperative Agreement No. 287E230009 with the Department’s Office of Elementary and Secondary Education. Opinions expressed herein do not necessarily reflect the position or policy of the Department, nor does mention of trade names, commercial products, or organizations imply endorsement by the Department or the federal government. This resource is in the public domain and is available at 21stcclcntac.org. Authorization to reproduce it in whole or in part is granted.

## 1. Overview - Subgrantee Name
Program Implementation Planner
Summer Program Leaders |  |  | Summer Program Logistics |  | Summer Program Participants
Program Director |  | Site Coordinator | Summer Site | Total Summer Budget | Total Students | 75 | Targeted Students | 130
Joe Smith |  | Jane Jacobs | ABC Elementary | 42350 | Criteria | Scored below proficiency on the summary skill on State standardized test | 0 | 0
Phone |  | Phone | Campuses Served | Meals | Summer Program Staff
555-555-5555 |  | 555-555-5555 | ABC Elementary | Breakfast | Admin | 1 | Volunteers | 3
Email |  | Email | LMN Elementary | Lunch | Certified | 2 | Paraprofessional | 1
joe@abc.edu |  | jane@abc.edu | QRS Elementary |  | Non-school day | 4 | Partner/Vendor | 2
Summer Program Schedule
Start Date |  | 2017-06-04 | End Date | 2017-07-27 | Total Weeks | 8 | Total Days | 31
Schedule |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Start Time |  | 9:00 | 9:00 | 9:00 | 9:00 | 0:00 | 0:00 | 0:00
End Time |  | 14:00 | 14:00 | 14:00 | 14:00 | 0:00 | 0:00 | 0:00
Program Mission and Vision
Vision |  | All students are happy, engaged, and learning.
Mission |  | Provide a high-quality summer learning program that meets the academic, social, emotional, and physical needs of all students.
Needs Statements
1 | About 93 percent of students at ABC Elementary receive free or reduced-price lunch.
2 | Only 37 percent of third graders met standards on language arts State assessment.
3 | 0
4 | 0
5 | 0
Summer Program Activities
|  | Activity | Activity | Activity | Activity | Activity | Activity | Notes
Intervention |  | Reading | 0 | 0 | 0 | 0 | 0
Academic Enrichment |  | Readers Theatre | Gardening | 0 | 0 | 0 | 0
Enrichment |  | Ceramics | Soccer | 0 | 0 | 0 | 0
College/Career |  | Robotics | 0 | 0 | 0 | 0 | 0
Family Engagement |  | Family Reading Picnic | 0 | 0 | 0 | 0 | 0
Program SMART Goals
1 | At least 80 percent of the learners will demonstrate proficiency in the skills of summary and inference on beginning-of-year benchmark assessments.
2 | 0
3 | 0
4 | 0
5 | 0
Note on B1: General Instructions – Overview: Remember to type in the blue areas only. Other sections will fill automatically based on your work in the other tabs.
Note on A2: Summer Program Leaders: It is important to keep this information up to date, as you will refer to this to plan data collection, communicate with stakeholders, and review program activities throughout the session.

## 2. Program Team Planner
Team Planner
Name | Role | Organization | Purpose for Participation | Contact Information
Joe Smith | Program director | ABC Learning Program | grant guidance, program leader | 555-555-5555, person@abc.edu
Jane Jacobs | Site coordinator | ABC Learning Program | program leader | 555-555-5555, person@abc.edu
Mary Lamb | Principal | ABC Elementary | connection with school day, access to data | 555-555-5555, person@abc.edu
Jim Bob | Third-grade teacher | ABC Elementary | connection with school day, access to data, feedback | 555-555-5555, person@abc.edu
Ebenezer Sams | Parent | Parent | input from families | 555-555-5555, person@xxx.com
Beth Brown | Student | Student | student voice | 555-555-5555, person@xxx.com
Wayne White | Partner | Theatre in Action | intentional design of program, feedback | 555-555-5555, person@xxx.com

## 3. Asset Mapping
Asset Mapping
| Needs | Resources | Notes
Community Resources | Access to a swimming pool | ABC Recreation Center | Use of swimming pool one day per week for 2 hours
Local Institutions | Additional staff (education majors) | Acme University | Providing three free education major staff in exchange for internship hours
Local Business | Plants and other gardening supplies | Local Garden Center | Free plants (slightly past prime) and three bags of free potting soil
Individuals | Assistance with gardening project | Joe Parker | Volunteer twice per week (Monday and Wednesday mornings) to help with garden; is a master gardener.
Note on A3: Community Resources: Recreation centers, parks, etc.
Note on A8: Local Institutions: Universities, libraries, museums, etc.
Note on A13: Local Business: Businesses, media outlets, etc.
Note on A18: Individuals: Family members, artists, senior citizens, etc.

## 4. Needs Assessment
Needs Assessment
Type | Data |  | Information Source | Notes
School Level | About 93 percent of students at ABC Elementary receive free or reduced-price lunch. |  | School Report Card
| Only 37 percent of third graders met standards on language arts State assessment. |  | Standardized Test Results
Student Level | Only 65 percent of third graders performed at passing level on reading questions related to summarization. |  | Standardized Test Results
| The third-grade teaching team reported that students who failed to meet standards on language arts State assessment were below proficiency on summary and inference skills. |  | Teacher Feedback
| About 57 percent of third graders reported being bullied within the past six months. |  | School Behaviors Survey
Student Voice | The top three interests reported by third graders were soccer, cooking, and dinosaurs. |  | Student Interest Inventory
| About 43 percent of third graders reported anxiety about the end-of-year standardized tests. |  | Student Focus Group
| Program SMART Goals | Associated Activity SMART Goals
1 | At least 80 percent of the learners will demonstrate proficiency in the skills of summary and inference on beginning-of-year benchmark assessments. | About 85 percent of students who attend the entire summer Readers Theatre activity will demonstrate increased proficiency in their ability to use summary and inference, as measured by journal writings.
About 85 percent of students who attend the entire summer language arts intervention will demonstrate increased proficiency in the use of summary and inference as measured by ABC software pre- and postsession assessments.
2
3
4
5
Note on A3: School Level: Data Source Examples: Campus or school improvement plans, school report cards, attendance and behavior reports
Note on A8: Student Level: Data Source Examples: Standardized test results, benchmark test results, feedback from teachers. Look for specific skill deficiencies, behaviors or trends.
Note on A13: Student Voice: Data Source Examples: Surveys, focus groups, reflection documents. Think about how to have students tell you what they want and need, and about ways to involve students in decision-making and governance.
Note on B18: Program SMART Goals: SMART Goals should be specific, measurable, achievable, relevant, and time bound. If you're stuck, try this template: The learners will ___ for the purpose of ___ as measured by ___. And don't forget to include a deadline.

## 5. Operations Planner
Operations Planner
Program Timeline
Start Date | 2017-06-04 |  | End Date | 2017-07-27 |  | Total Number of Weeks |  |  | 8 |  | Total Hours Per Week |  | 20
Program Schedule/Hours
| Monday |  | Tuesday |  | Wednesday |  | Thursday |  | Friday |  | Saturday |  | Sunday
Start Time | 9:00 |  | 9:00 |  | 9:00 |  | 9:00
End Time | 14:00 |  | 14:00 |  | 14:00 |  | 14:00
Scheduled Meal Times
Breakfast | 9:00 |  |  | Lunch | 12:30 |  |  | Snack |  |  |  | Supper
Program Operations Chart
Site |  |  |  |  | ABC Elementary
Address |  |  |  |  | 1234 Main Avenue
Phone Number |  |  |  |  | 555-555-5555
Summer Program Director |  |  |  |  | Joe Smith
Summer Site Coordinator |  |  |  |  | Jane Jacobs
Summer School Principal (if applicable) |  |  |  |  | Mary Lamb
Participating Campuses/Sites |  |  |  |  | ABC Elementary |  | LMN Elementary |  | QRS Elementary
Program Enrollment
Total Program Capacity |  |  | 75 |  |  | Total Students Targeted |  |  | 130
Enrollment Goals by Grade Level |  | K= | 1= | 2= | 3=25 | 4=25 | 5=25 | 6= | 7= | 8= | 9= | 10= | 11= | 12=
Program Space
Spaces Used (e.g., gym, cafeteria, Room 102) |  |  |  |  | Cafeteria | Gym | Library | Computer Lab | Art Room | Room 352
Most activities will happen on site? (Yes/No) |  |  | Yes |  | Adjunct Sites (if any) |  | NextDoor Recreation Center |  |  | Transportation provided (Yes/No) |  |  | Yes

## 6. Budget Planner
Budget Planner
Summer Learning Program Budget
Category | Grant Funded | Other Funding | Funding Source | Notes
Personnel
Site coordinator | 4000 |  | 21st CCLC
Certified teachers | 8000 |  | 21st CCLC
Youth workers | 7000 |  | 21st CCLC
Total Personnel | 19000
Contractual
Student transportation | 15000 |  | 21st CCLC
Field trips | 2000 |  | ABC Foundation
Total Contractual | 17000
Travel/Training
Travel | 500 |  | 21st CCLC
Training | 1500 |  | DEF Grant
Total Travel/Training | 2000
Supplies
Miscellaneous | 1500 |  | 21st CCLC
Benefits
15% of salary for full-time extra duty staff | 2850 |  | 21st CCLC
Total Budget | 42350
Note on A1: General Instructions: Modify this tab as needed to fit your summer program budget.

## 7. Program Schedule
Program Schedule
ABC Summer Learning Program
Monday
Times | Group 1: Third Grade |  |  |  | Group 2: Fourth Grade |  |  |  | Group 3: Fifth Grade
| Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space
9:00-9:30 | Breakfast |  | All Staff | Cafeteria | Breakfast |  | All Staff | Cafeteria | Breakfast |  | All Staff | Cafeteria
9:30-10:30 | Gardening |  | Betty | Outdoor Garden | Reading |  | Bob | Room 352 | Robotics |  | Samantha | Library
10:30-11:30 | Reading |  | Bob | Room 352 | Ceramics |  | Betty | Art Room | Soccer |  | Joe | Field
11:30-12:30 | Cooking |  | Samantha | Art Room | Soccer |  | Joe | Field | Reading |  | Bob | Room 352
12:30-1:00 | Lunch |  | All Staff | Cafeteria | Lunch |  | All Staff | Cafeteria | Lunch |  | All Staff | Cafeteria
1:00-2:00 | Soccer |  | Joe | Field | Robotics |  | Samantha | Library | Gardening |  | Betty | Outdoor Garden
Tuesday
Times | Group 1 |  |  |  | Group 2 |  |  |  | Group 3
| Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space
11:00-11:30
11:30-12:30
12:30-1:30
1:30-2:30
2:30-3:30
3:30-4:00
Wednesday
Times | Group 1 |  |  |  | Group 2 |  |  |  | Group 3
| Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space
11:00-11:30
11:30-12:30
12:30-1:30
1:30-2:30
2:30-3:30
3:30-4:00
Thursday
Times | Group 1 |  |  |  | Group 2 |  |  |  | Group 3
| Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space
11:00-11:30
11:30-12:30
12:30-1:30
1:30-2:30
2:30-3:30
3:30-4:00
Friday
Times | Group 1 |  |  |  | Group 2 |  |  |  | Group 3
| Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space | Activity Name | Description | Staff | Space
11:00-11:30
11:30-12:30
12:30-1:30
1:30-2:30
2:30-3:30
3:30-4:00
Note on A1: General Instructions: Modify this tab as needed to fit your summer program schedule.

## 8. Field Trip Planner
Field Trip Planner
Location | Date | Depart Site Time | Arrive Location Time | Depart Location Time | Arrive Site Time | Cost | Food | Contact Name | Contact Number/Email | Intentional Design | Notes
Zoo | 2018-07-02 | 9:45 | 10:00 | 14:00 | 14:15 | $3 per child per day (due the following Thursday) | Brown bag lunch at zoo | Felicia Smithers | 555-555-5555, felicia@abc.edu | Targeted knowledge or skill: Using summary and inference Students will have a guided tour of the zoo. Leaders will use guiding questions to help students use inferencing skills. Back at the program site, students will choose their favorite animal and write a summary paragraph describing what they learned about the animal.
Note on K2: Intentional Design: What is the purpose of this field trip? How is it tied to your program SMART goals?

## 9. Intentional Design Planner
Intentional Design Planner
Program SMART Goal | Want: Student Voice | Activity | Intentional Design Description | Activity SMART Goal | Learning Method | Learning Strategy | 21st Century Skill | Positive Youth Development
80% of the learners will demonstrate proficiency in summary and inference on beginning of year benchmark assessments. | Cooking | Readers Theatre | Students will read parts of fairy tales, and a facilitator will guide them to make inferences about how the story might end. When they complete a story, they will write a summary of the story in their journal. Students will then work together to create a new ending for the fairy tale and perform the story on stage for their peers. | About 85 percent of students who attend the entire summer Readers Theatre activity will demonstrate increased proficiency in their ability to use summary and inference as measured by journal writings. | Themed Learning |  | Collaboration | Competence
Note on A2: Program SMART Goal: Copy and paste your program SMART goals from the Needs Assessment tab.
Note on B2: Want: Student Voice: Pull this information from the Needs Assessment tab.
Note on D2: Intentional Design Description: How will you blend what the students need (the program SMART goal) with what they want (the student voice)?
Note on E2: Activity SMART Goal: Make sure to transfer your activity SMART goals onto the Needs Assessment tab beside the associated program SMART goal.
Note on F2: Learning Method: Project-based learning Problem-based learning Service learning Blended learning Place-based learning Themed learning
Note on G2: Learning Strategy: Learning Centers Genius Hour Interactive Notebook Mind Mapping Reciprocal Teaching
Note on H2: 21st Century Skill: Critical Thinking Communication Collaboration Creativity
Note on I2: Positive Youth Development: Competence Confidence Connection Character Caring

## 10. Staffing Planner
Staffing Planner
Activity Name | Day of Week | Time | Type of Instructor | Other Pertinent Qualifications | Possible Instructors | Notes
Gardening | Mon, Wed | 9:30-2:00 | Any | Experience gardening | Betty
Reading Intervention and Readers Theatre | Mon-Fri | 9:30-2:00 | Teacher | Certified elementary or reading teacher | Bob
Cooking | Mon, Wed | 9:30-2:00 | Any | Experience cooking | Samantha
Soccer | Mon-Thur | 9:30-2:00 | Any | Knowledge of soccer rules, coaching experience | Joe
Ceramics | Mon, Wed | 9:30-2:00 | Any | Experience with ceramics | Betty
Robotics | Mon, Wed | 9:30-2:00 | Teacher | Certified robotics teacher | Samantha

## 11.Intentional Recruitment Plan
Intentional Recruitment Plan
Enrollment Criteria
Level 1 – Must Haves |  | Level 2 – Should Haves
Scored below proficiency on the summary skill on State standardized test |  | Considered "at-risk"
Intentional Recruitment Plan
Strategy | Action Steps | Materials/Costs | Responsible Person | Completion Date
Send brochure that describes the summer program and benefits of participation to all 130 targeted students. | 1. Create informative brochure. 2. Print and address 130 brochures to mail to homes and 130 to distribute to students. | $20 paper, $20 printing | Betty - design Jane - printing, mailing, and distribution | Design: March 1 Mail: March 15 Distribute: March 30

## 12. Logic Model
Logic Model
Inputs | Outputs |  |  | Short-Term Outcomes | Long-Term Outcomes
| Categories | Activities | Participation | (SMART Goals)
1 Site coordinator | Academic Intervention | Reading
2 Certified teachers
1 Robotics curriculum
Access to 6 areas within ABC Elementary
| Academic Enrichment | Readers Theatre | All third-grade students, two days per week, one hour per day | About 85 percent of students who attend the entire summer Readers Theatre activity will demonstrate increased proficiency in their ability to use summary and inference, as measured by journal writings. | At least 80 percent of the learners will demonstrate proficiency in summary and inference on beginning-of-year benchmark assessments.
Gardening
| Enrichment | Ceramics
Soccer
| College and Career | Robotics
| Family Engagement | Family Reading Picnic
Note on A2: Inputs: This is one long list of inputs and does not have to correlate across the row with anything specifically.
Note on E2: Short-Term Outcomes: These are your activity SMART goals.
Note on F2: Long-Term Outcomes: These are your program SMART goals or overall grant goals.
Note on C3: Outputs - Activities: Classes added here will also populate your Overview page.
Note on D3: Outputs - Participation: How many students? Which students? How many days per week? How many hours or minutes per day?

## 13. Continuous Improvement
Continuous Improvement Planner
Performance Measures | Measurement Tool | Staff Assigned | Target Group | Time Frame | Actual Outcomes
Enter program SMART Goals | What will be used to measure effectiveness? | Who is responsible for collecting or tracking data? (Include name or title) | Who is being assessed? (Enter the name or group) | When will measurements be taken? | What did the data tell you? Restate your SMART goal using actual measurements.
At least 80 percent of the learners will demonstrate proficiency in the skills of summary and inference on beginning-of-year benchmark assessments. | Portfolio of written summaries | Bob, teacher | All summer program students | At least one summary per week, with final assessment completed by August 1 | About 70 percent of the learners demonstrated proficiency in summary and inferencing as measured by beginning-of-year benchmark assessments.
0
0
0
0
Enter activity SMART Goals | What will be used to measure effectiveness? | Who is responsible for collecting or tracking data? (Include name or title) | Who is being assessed? (Enter the name or group) | When will measurements be taken? | What did the data tell you? Restate your SMART goal using actual measurements.
About 85 percent of students who attend the entire summer Readers Theatre activity will demonstrate increased proficiency in their ability to use summary and inference as measured by journal writings. | Journals and performance rubric | Samantha, teacher | All third-grade students | At the end of class each day (Mon & Wed) | About 90 percent of students who attended the entire summer Readers Theatre demonstrated increased proficiency in the ability to use summary and inferencing.
0
0
0
0
0
0
0
0
Note on F2: Actual Outcomes: This will be completed after your summer program ends.
Note on A3: Performance Measures - Enter program SMART goals: These will prefill from the Needs Assessment tab.
Note on A9: Performance Measures - Enter activity SMART goals: These will prefill from the Intentional Design tab.